## Priority Matrix
THE ELDER — Unknown Unknowns Priority Matrix
AHAU AI / Temporal Bridges Institute · Items to be resolved before public launch
Done | # | Item | Tier | Domain | Stakes | Status
☐ | 1 | CROSS-03 Pythia gap + 5 probe signal expansions (never applied post-factory-reset) | Tier 1 — Structural Integrity | Security / Lineage Integrity | Active security hole — confirmed system prompt gap allows cross-tradition combination | 🔴 Not applied to cloned repo
☐ | 2 | Chol Q'ij TypeScript engine validation against Python module (500+ dates, anchor 5 Kawoq) | Tier 1 — Structural Integrity | Calendar / Ceremonial Accuracy | Seekers may be receiving incorrect Cruz Maya positions — ceremonial error, not UX error | 🔴 Script never built
☐ | 3 | Babalawo authentication session artifacts: offline signing tool, preflight hash-match gate, extended contract schema | Tier 1 — Structural Integrity | Lineage Authentication | Blocks Yorùbá voice activation — session with Kingsley's mother cannot proceed without these | 🔴 Designed; artifacts not built
☐ | 4 | Altar Record persistent storage — replace writeSignal() stub with live backend (Google Sheets webhook or Neon) | Tier 2 — Observability | Session Analytics | No visibility into whether ⟡⟡READY⟡⟡ fires, seeker drop-off, or crisis detection triggers | 🟠 Stub only (localStorage)
☐ | 5 | Post-Reading feedback mechanism — closing gesture + seeker signal after Ceremonial Charge | Tier 2 — Observability | UX / Quality Signal | Reading ends into void; no quality signal on diagnostic accuracy; no ceremonial closing | 🟠 Never designed
☐ | 6 | Stanzione corpus markup session — run ingest.py + schema.sql to ground K'iche' transmission layer | Tier 3 — Governance Infrastructure | Lineage / Corpus | corpusVersion returns 'pre-markup'; every K'iche' reading is ungrounded at the passage level | 🟠 Scripts ready; session not held
☐ | 7 | Babalawo infrastructure vulnerabilities V1–V6 (key custody, revocation, corpus drift, scope, draft leakage, single-elder fragility) | Tier 3 — Governance Infrastructure | Lineage Authentication | Elder consent cannot be honored correctly without this infrastructure | 🟠 Designed; not built
☐ | 8 | DATABASE_URL / Neon provisioning — log/route.ts silently skips all INSERTs without this | Tier 3 — Governance Infrastructure | Infrastructure | No server-side logging; provenance chain ends at localStorage | 🟠 Unprovisioned
☐ | 9 | Consent and scope-of-use product layer — age affirmation, scope statement, data retention policy, Maya community acknowledgment, ToS | Tier 4 — Legal & Consent | Legal / Launch Gate | Gates any expansion beyond named-cohort beta; existential on a vulnerable-user event | 🔴 Prose only; nothing built into product
☐ | 10 | Returning seeker design — philosophy surfaced to seeker, continuity layer or divergence handling | Tier 4 — Legal & Consent | UX / Ceremony | Experience breaks silently for returning seekers who receive conflicting myths | 🔴 Never designed
☐ | 11 | 7 voices with zero adversarial coverage — programmatic probe generation from tradition matrix | Tier 5 — Hardening | Security / Lineage Integrity | Sufi, Vedic, Egyptian, Dreamtime, Greek, Taoist, Yorùbá have no cross-tradition contamination tests | 🟡 Not built
☐ | 12 | Generative probe layer — independent LLM generating novel attack variants beyond static 27 probes | Tier 5 — Hardening | Security | Static probes are a known exam; most dangerous attacks are the ones not yet written | 🟡 Not built
☐ | 13 | Statistical probe reliability — N=3 minimum per probe with pass rate reporting, not binary pass/fail | Tier 5 — Hardening | Security | Single-run execution gives false confidence; LLMs are probabilistic | 🟡 Not built
☐ | 14 | ELDER_MODEL_VERSION env var — collapse second source of truth into direct PRIMARY_MODEL import | Tier 5 — Hardening | Infrastructure | Will silently diverge from model.config.ts on next model upgrade | 🟡 ADR noted; not resolved
☐ | 15 | Staging branch — dev → main via PR gate to prevent single push breaking live ceremony | Tier 5 — Hardening | Infrastructure | Every push currently deploys directly to production | 🟡 Not created
Completed: |  | 0 / 15 items |  | Mark items ☑ in column A as each is completed